ARCHIVE-35

Hospitality Art Market — Action Plan

Weekly Sprints • Wolf + Claude Working Together

HOW THIS WORKS:  Each sprint = 1 week. Tasks marked Wolf = you do it. Claude = I draft/research it for you. Both = we work on it together in chat. Check the box when done.

# SPRINT 1: Portfolio & Platform Prep

Goal: Get your portfolio hospitality-ready and submitted to the top 4 platforms that control hotel art placement.

| ✓ | TASK | DETAILS / LINKS | WHO |
| --- | --- | --- | --- |
| □ | Create hospitality portfolio page on archive-35.com | Add a “For Designers & Hotels” page. Show panoramas at scale, licensing terms, large-format capability. | Both |
| □ | Create mock-ups of art in hotel settings | Use Photoshop/Canva to place your best images into lobby, corridor, guest room settings. 6-8 mock-ups. | Wolf |
| □ | Write artist bio for hospitality submissions | Short version (100 words) + long version (300 words). Emphasize 25 years, 55+ countries, music touring angle. | Claude |
| □ | Prepare pricing & licensing guide | One-pager: print sizes, price ranges, licensing for volume reproduction (guest rooms need 100+ of same image). | Both |
| □ | Submit to Indiewalls | artwork.indiewalls.com/artist — Resume + portfolio. #1 priority platform (Marriott preferred vendor). | Wolf |
| □ | Submit to NINE dot ARTS | Apply via callforentry.org (search “Nine Dot Arts”) + create free ArtCloud portfolio (artcloud.com). | Wolf |
| □ | Submit to Kalisher | kalisher.com/submit-your-work — 3 images, bio, pricing guide. CHECK the licensing box. | Wolf |
| □ | Create Saatchi Art artist profile | saatchiart.com — Free profile, upload high-res images. LA-based, works with Nobu, Four Seasons, Tommie Hollywood. | Wolf |

# SPRINT 2: Tier 2 Submissions + LA Research

Goal: Complete all remaining platform submissions and start mapping the LA hospitality art landscape.

| ✓ | TASK | DETAILS / LINKS | WHO |
| --- | --- | --- | --- |
| □ | Submit to Tappan Collective | submissions@thetappancollective.com — Bio, artist statement, CV, website link, PDF of available works. LA-based (Melrose gallery). | Wolf |
| □ | Submit to Uprise Art | submissions@upriseart.com — NYC-based, hospitality + commercial. Trade: trade@upriseart.com. | Wolf |
| □ | Submit to Graphic Encounter Fine Art | Email 20 images as PDF/JPEG (1000px, 144-300 dpi) to Culver City office. They reach 45K+ designers. | Wolf |
| □ | Research Morrison Hotel Gallery | 310.881.6025 — Sunset Marquis lobby. World’s top music photo gallery. Explore representation or collaboration. | Both |
| □ | Draft outreach email for art consultants | Template pitch email for LA-based art consultants. Music touring angle + panoramic specialty + licensing. | Claude |
| □ | Map 5 LA boutique hotels to visit | Research current art at: Hotel Ziggy, The LINE LA, Palihouse, Hotel Figueroa, Proper Hotel. Who did their art? | Claude |
| □ | Contact KBAA (Kevin Barry Art Advisory) | kevinbarry.com — LA, SF, Vegas offices. 20+ consultants. Works with Four Seasons, Hilton, Marriott. | Both |
| □ | Contact Fresh Paint Art Advisors | freshpaintart.com — 40+ years in LA. Committed to emerging talent. | Both |

# SPRINT 3: In-Person Recon + Designer Outreach

Goal: Get out of the house. Walk into boutique hotels, gather intel, and start contacting interior design firms.

| ✓ | TASK | DETAILS / LINKS | WHO |
| --- | --- | --- | --- |
| □ | Visit 3 LA boutique hotels (recon walks) | Walk in, study the art, ask front desk: “Who manages art here?” If GM is free, introduce yourself. Leave portfolio card. | Wolf |
| □ | Document what you see (photos + notes) | Photograph art placements, note sizes, styles, framing. This becomes market intel for your pitch. | Wolf |
| □ | Contact Curate Art Group | curateartgroup.com — Handles Hilton Santa Monica, Sunset Tower, Four Seasons Westlake, Ojai Valley Inn. | Both |
| □ | Contact WRAPPED Studios | wrappedla.com — Venice Beach. Did art for Omni Hotels. They collaborate with outside artists. | Both |
| □ | Contact Anne Mennealy Art Advisory | amennealy.com — 30+ years LA hospitality art advisory. | Both |
| □ | Draft outreach email for interior designers | Template for firms like HBA, Rockwell Group. Reference specific projects. Story-first approach. | Claude |
| □ | Contact HBA Art (Los Angeles office) | hba.com/expertise/art — World’s biggest hospitality design firm. Dedicated art consultancy division. | Both |
| □ | Research HD Summit (March 11-13, San Diego) | Invitation-only event at Hotel del Coronado. Can we get you in? Worth exploring. | Claude |

# SPRINT 4: Trade Show Planning + Follow-Ups

Goal: Lock in trade show strategy for 2026 and follow up on all initial outreach.

| ✓ | TASK | DETAILS / LINKS | WHO |
| --- | --- | --- | --- |
| □ | Follow up on all platform submissions | Check status on Indiewalls, NINE dot ARTS, Kalisher, Saatchi, Tappan, Uprise, Graphic Encounter. | Wolf |
| □ | Follow up with all contacted art consultants | KBAA, Fresh Paint, Curate, WRAPPED, Anne Mennealy, HBA Art. 2nd touch if no response. | Both |
| □ | Research HD Expo exhibitor costs | May 5-7, 2026, Mandalay Bay, Vegas. Inquiry: hdexpo.hospitalitydesign.com. “Accessories + Art” category. | Claude |
| □ | Research BDNY exhibitor costs | Nov 8-9, 2026, Javits Center, NYC. Inquiry: bdny.com. Gallery-style booths. #1 priority show. | Claude |
| □ | Research BITAC Purchasing & Design | Oct 25-27, 2026, Carlsbad, CA. Meeting-format event connecting buyers with suppliers. Close to LA. | Claude |
| □ | Decide: which trade shows to attend vs. exhibit | Budget check. Attending = networking ($free-$500). Exhibiting = booth ($3K-$15K+). Prioritize. | Both |
| □ | Create physical portfolio / leave-behind | Design a printed mini-portfolio or high-quality postcard set for in-person meetings and hotel visits. | Both |
| □ | Update archive-35.com with any early wins | If any platforms accept you, add “As seen on Indiewalls / Saatchi Art” badges to your site. | Wolf |

# SPRINTS 5-8: Scale & Branded Residences

Goal: Expand beyond LA. Target branded residences and national design firms. These are longer-term plays.

| ✓ | TASK | DETAILS / LINKS | WHO |
| --- | --- | --- | --- |
| □ | Research active branded residence projects | Four Seasons Las Vegas, St. Regis Miami, Aman Beverly Hills, Mandarin Oriental Miami. Who’s doing the art? | Claude |
| □ | Contact Rockwell Group (NYC/LA) | Doing interiors for St. Regis Miami + Ritz-Carlton West Palm Beach. Major art-forward firm. | Both |
| □ | Contact Kelly Wearstler (LA) | Proper Hotels, Four Seasons Anguilla, Waldorf Astoria Beverly Hills. LA-based. High-end. | Both |
| □ | Contact WATG/Wimberly Interiors (Irvine) | Doing Four Seasons Private Residences Las Vegas. Completion late 2026 — art not yet finalized. | Both |
| □ | Explore Maison & Objet Paris (Jan 2027) | Free exhibition space for emerging brands via “Future On Stage” program. Worth applying. | Claude |
| □ | Target music-themed hotels specifically | Morrison Hotel Gallery, Hotel Ziggy, The Verb (Boston), Hotel Max (Seattle), Hotel Saint Cecilia (Austin). | Both |
| □ | Pitch Related Group (Miami developer) | Founder Jorge Pérez = top art collector. They buy art specifically for condo projects. 700+ piece collection. | Both |
| □ | Attend Art Basel Miami (Dec 2026) | $55-85 day pass. Network at satellite fairs (SCOPE, UNTITLED). Hotel art consultants attend heavily. | Wolf |

# QUICK REFERENCE: Key Contacts

Keep this page handy. These are the people and platforms that matter most.

## Art Consulting Platforms (Submit To)

| PLATFORM | SUBMISSION URL | WHY IT MATTERS |
| --- | --- | --- |
| Indiewalls | artwork.indiewalls.com/artist | Marriott preferred vendor. $9M+ paid to artists. |
| NINE dot ARTS | callforentry.org + artcloud.com | 1,000+ projects. 10K artist network. |
| Kalisher | kalisher.com/submit-your-work | Marriott, Hilton, Hyatt. Check licensing box. |
| Saatchi Art | saatchiart.com (create profile) | LA-based. Nobu, Four Seasons, Tommie. |
| Tappan Collective | submissions@thetappancollective.com | LA gallery. Hospitality advisory team. |
| Uprise Art | submissions@upriseart.com | NYC. Hospitality + commercial. |
| Graphic Encounter | Email 20 images to Culver City office | 45K+ designer reach. Since 1970. |

## LA Art Consultants (Contact Directly)

| FIRM | WEBSITE | KEY HOTEL CLIENTS |
| --- | --- | --- |
| KBAA | kevinbarry.com | Four Seasons, Hilton, Marriott (LA/SF/Vegas) |
| Fresh Paint Art Advisors | freshpaintart.com | 40+ years LA. Major hotel brands. |
| Curate Art Group | curateartgroup.com | Hilton Santa Monica, Sunset Tower, Ojai Valley Inn |
| WRAPPED Studios | wrappedla.com | Omni Hotels, Hotel Crillon Paris |
| Anne Mennealy | amennealy.com | 30+ years LA hospitality advisory |
| HBA Art | hba.com/expertise/art | Ritz-Carlton, Four Seasons (global) |
| Morrison Hotel Gallery | 310.881.6025 | Sunset Marquis. Music photo specialists. |

## 2026 Trade Shows (Calendar)

| WHEN | EVENT | WHERE | ACTION |
| --- | --- | --- | --- |
| Mar 11-13 | HD Summit | San Diego (Hotel del Coronado) | Network (invitation-only) |
| May 5-7 | HD Expo | Las Vegas (Mandalay Bay) | Attend or Exhibit |
| Oct 25-27 | BITAC Purchasing | Carlsbad, CA | Attend (meeting format) |
| Nov 8-9 | BDNY | NYC (Javits Center) | EXHIBIT — #1 priority |
| Dec TBD | Art Basel Miami | Miami Beach | Attend + network |

NEXT STEP:  Open a new chat when you’re ready to start Sprint 1. Say “Let’s work on Sprint 1” and we’ll knock out each task together — I’ll draft emails, research contacts, build pitch decks, whatever you need.